## Sheet1
Month | October |  |  |  | November
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
DEFINE
Coding Environment/Github Creation
Code Initialization
Initial Proposal Template Creation
Initial Proposal Work
Initial Proposal Submission |  | Sun Oct. 9
BUILD
Data Load + Cleaning
Variable Discovery/ Identification
Model Creation
Model Testing
Visualization
Progress Template Creation
Progress Report Work
Progress Video Work
Progress Video/Report Submission |  |  |  |  | Sun Oct. 30
ANALYZE
Final Report Templates Creation
Final Report Video Work
Final Report Materials Work
Final Report Video Submission | [8 empty] | Wed Nov 16
Final Report Materials Submission | [8 empty] | Sun Nov 20
Peer Reviews/Teammate Evaluation | [8 empty] | Wed Nov 23